# <Project Name>

# Software Development Plan (Small Project)

# Version <1.0>

# Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 18/Oct/26 | 1.0 | Initial draft for the Inception phase (PA1) | Team 11 |

# Table of Contents

1.	Introduction 4

1.1	Purpose 4

1.2	Scope 4

1.3	Overview 4

2.	Project Overview 4

2.1	Project Purpose, Scope, and Objectives 4

2.2	Assumptions and Constraints 4

2.3	Project Deliverables 5

3.	Project Organization 5

3.1	Organizational Structure 5

3.2	Roles and Responsibilities 5

4.	Management Process 5

4.1	Project Estimates 5

4.2	Project Plan 5

4.2.1	Phase Plan 5

4.2.2	Iteration Objectives 6

4.2.3	Releases 6

4.2.4	Project Schedule 6

4.2.5	Project Resourcing 6

4.3	Project Monitoring and Control 6

4.3.1	Requirements Management 6

4.3.2	Reporting and Measurement 7

4.3.3	Risk Management 7

4.3.4	Configuration Management 7

# Software Development Plan (Small Project)

# Introduction

## Purpose

This document describes how our team plans, organizes and monitors the development of Trozy, a web application that helps boarding house landlords and tenants manage rooms, utility bills and maintenance requests with the help of AI. It is the initial version written in the Inception phase. It will be reviewed by the TAs and updated in PA2.

The purpose of the Software Development Plan is to gather all information necessary to control the project. It describes the approach to the development of the software and is the top-level plan generated and used by managers to direct the development effort.

The following people use the Software Development Plan:

- The project manager uses it to plan the project schedule and resource needs, and to track progress against the schedule.

- Project team members use it to understand what they need to do, when they need to do it, and what other activities they are dependent upon.

## Scope

The plan covers the whole project from 5/10/2026 to 13/12/2026, divided into five two-week sprints. It applies to all team members, and to all project documents and source code.

This Software Development Plan describes the overall plan to be used by the <project name> project, including deployment of the product. The details of the individual iterations will be described in the Iteration Plans.
The plans as outlined in this document are based upon the product requirements as defined in the Vision Document.

## Overview

Section 2 gives an overview of the project. Section 3 describes the team organization, roles and communication. Section 4 describes the phase plan, builds, schedule, requirements management and risk management.

This Software Development Plan contains the following information:

Project Overview — provides a description of the project's purpose, scope, and objectives.  It also defines the deliverables that the project is expected to deliver.

Project Organization — describes the organizational structure of the project team.

Definitions, Acronyms and Abbreviations

| Term | Meaning |
| --- | --- |
| AI | Artificial Intelligence |
| API | Application Programming Interface |
| Build | A tested version of the software deployed for testing |
| CCCD | Vietnamese citizen identity card number |
| MVP | Minimum Viable Product |
| OCR | Optical Character Recognition, reading text or digits from an image |
| PA | Project Assignment |
| PDPL | Vietnam Law on Personal Data Protection (2025) |
| PWA | Progressive Web App, a website that can be installed on a phone |
| RUP | Rational Unified Process (Inception, Elaboration, Construction phases) |
| Sprint | A two-week iteration in Scrum |
| TA | Teaching Assistant |
| VietQR | Standard QR code used for bank transfers in Vietnam |

References

- PA0: Group Registration and Tools Setup

- PA1: Project Assignment 1

- Project proposal and interview notes (PA0)

- Vision Document v1.0 (PA1)

- Law on Personal Data Protection 2025 (Law No. 91/2025/QH15) and Decree 356/2025/ND-CP

# Project Overview

## Project Purpose, Scope, and Objectives

Purpose. Many small landlords in Vietnam (roughly 5 to 30 rooms) still record electricity and water readings, calculate invoices and track payments with notebooks, Excel or Zalo messages. Doing this by hand each month is slow and error-prone, and mistakes lead to disputes with tenants. Existing apps cover most general management features, but not AI-assisted meter reading. Trozy fills this gap and adds further AI features that benefit both landlords and tenants.

Objectives.

| ID | Objective | Measure of success |
| --- | --- | --- |
| O1 | Deliver a working web app that covers the full monthly cycle: room, tenant, meter reading, invoice, payment | Full cycle demonstrated on test data at the end of Sprint 5 |
| O2 | Provide AI-assisted meter reading from photos | OCR with image-quality check, validation and manual fallback; target at least 90% correct reads on good-quality photos in our own test set of at least 100 photos |
| O3 | Provide AI differentiators: usage anomaly alerts and smart issue reporting | Both features demonstrated in the final build |
| O4 | Protect personal data by design | Minimum data collected; ID numbers encrypted; consent recorded; no ID card images stored |
| O5 | Practice professional teamwork | All tasks tracked in Jira, code merged through GitHub pull requests, weekly reports submitted on time |

In scope: account and role management; house, room, tenant and contract management; utility rate configuration; meter reading by photo; automatic invoices; QR payment tracking; reminders and notifications; anomaly alerts; issue reporting with AI triage; dashboard and reports; privacy functions.

Out of scope: real payment gateway integration, electronic contracts with digital signatures, in-app chat, storing images of ID cards, native mobile apps (stretch goal only).

## Assumptions and Constraints

Assumptions

- Team members are beginners in software development and will learn the technology during the project.

- Each member can spend about 8 to 10 hours per week on the project.

- Free tiers of cloud hosting and AI APIs are enough for development and demo.

- Only synthetic (fake) data is used for testing and demo.

Constraints

- Fixed deadlines: PA1 on 18/10, final build on 13/12/2026.

- Team of 3 to 5 students and zero budget.

- Mandatory tools: Moodle, Facebook group, Jira, GitHub with the required folder structure.

- Compliance with Vietnamese personal data protection law.

## Project Deliverables

| Assignment | End of | Main deliverables |
| --- | --- | --- |
| PA1 | Sprint 1 (18/10) | Project plan v1, Vision document v1, 3 to 6 UI sketches, 2 weekly reports |
| PA2 | Sprint 2 (1/11) | Updated plan and vision, requirements (use cases), initial architecture and design, Build 0 |
| PA3 | Sprint 3 (15/11) | Detailed design, test plan, Build 1 |
| PA4 | Sprint 4 (29/11) | Build 2, test cases and test report |
| PA5 | Sprint 5 (13/12) | Final build, final documents, user guide, demo |

Evolution of the Project Plan

The plan is reviewed at every sprint planning meeting and updated when scope, schedule or team changes. The version after TA feedback will be submitted in PA2. Every change is recorded in the revision history and the old version stays in GitHub (/docs/management).

# Project Organization

## Organizational Structure

The team is flat and self-organized, following Scrum. The group leader acts as Project Manager and Scrum Master. One member acts as Product Owner for requirements and priorities. All members take part in development and testing. The instructor and TAs act as reviewers and approve the project direction.

External Interfaces and Communication

| Party | Interaction | Channel | Frequency |
| --- | --- | --- | --- |
| Instructor and TAs | Review proposal and deliverables, give feedback | Moodle, lab sessions | Every sprint |
| Potential users (landlords, tenants) | Interviews, feedback on UI sketches and builds | Meetings, calls, forms | At least 5 interviews in Sprint 1, feedback each sprint |
| AI service provider | Vision and language API used for meter reading and issue triage | HTTPS API | Runtime |

Tools

| Tool | Purpose |
| --- | --- |
| Moodle | Submit assignments |
| Facebook group | Class announcements and Q&A |
| Jira | One board for the group, tasks organized in sprints |
| GitHub | Source control with folders /src, /docs (management, requirements, analysis and design, test) and /pa |

Team meetings and tracking. Sprint planning on the first day of each sprint (1 hour). Two short team meetings per week (30 minutes) to review the board and risks. Daily progress notes in the Zalo channel. Sprint review and retrospective on the last day. One weekly report per week, stored in /docs/management. Progress is read from the Jira board.

## Roles and Responsibilities

If the team has fewer than five members, adjacent roles are merged.

| Person | Role |
| --- | --- |
| [Name], group leader | Project Manager and Scrum Master (PM) Maintains the plan and Jira board, runs meetings, tracks progress and risks, writes weekly reports, communicates with TAs, packages submissions |
| [Name] | Product Owner and Business Analyst (BA) Conducts interviews, writes the vision document and use cases, maintains the feature list and priorities, answers requirement questions |
| [Name] | Architect and Backend/AI Developer (BE) Chooses the architecture and tech stack, designs database and API, implements backend and AI integration (OCR, anomaly alerts, issue triage), manages the repository and deployment |
| [Name] | Frontend and UI/UX Developer (FE) Creates UI sketches and wireframes, implements the web interface, integrates with the API, checks usability |
| [Name] | Tester and Documentation (QA) Writes the test plan and test cases, tests each build, reports bugs in Jira, collects the OCR test photo set, maintains test and user documents |

All members implement features, review each other's pull requests and fix bugs. The tester does not own production code, but writes test scripts and verifies fixes.

| Person | Role |
| --- | --- |
| Sally Slalom, Senior Manager |  |
| Matt Mogul, VP Operations |  |
| Tom Telemark, Senior Software Engineer |  |
| Susan Snow, Software Engineer Henry Halfpipe, Junior Software Engineer TBD1, Software Engineer TBD2, Junior Software Engineer |  |
| Patrick Powder, Administrative Assistant | Responsible for maintaining the Project web site, assisting the Project Manager role in planning/scheduling activities, and assisting the Change Control Manager role in controlling changes to artifacts. May also provide assistance to other roles as necessary. |

# Management Process

## Project Estimates

[Provide the estimated cost and schedule for the project, as well as the basis for those estimates, and the points and circumstances in the project when re-estimation will occur.]

## Project Plan

[This section contains the schedule and resources for the project.]

### Phase Plan

The project has three phases and five sprints, consistent with the course schedule.

| Phase | Sprints | Dates | Objectives | Milestone |
| --- | --- | --- | --- | --- |
| Inception | Sprint 1 | 5/10 to 18/10 | Form the team, set up tools, choose the project, interview users, write initial plan, vision and UI sketches | Agreed vision, scope and plan (PA1) |
| Elaboration | Sprint 2, Sprint 3 | 19/10 to 15/11 | Define requirements, design architecture and database, write test plan, build the core of the system | Requirements baselined, architecture proven by a working build (PA2, PA3) |
| Construction | Sprint 4, Sprint 5 | 16/11 to 13/12 | Implement AI features and the remaining functions, test, fix bugs, finish documents | Final tested product and demo (PA4, PA5) |

### Iteration Objectives

We will produce four builds. Each build is created from the main branch, tagged in GitHub, deployed to a staging environment and checked with a smoke test before the team tests it.

| Build | Date | Content | Purpose |
| --- | --- | --- | --- |
| Build 0 | 1/11 (end of Sprint 2) | Technical skeleton: sign up, login, role-based home page, one working CRUD (rooms), database, automatic build | Prove that the chosen technology works end to end |
| Build 1 | 15/11 (end of Sprint 3) | Accounts and roles with consent, house and room management, tenant and contract management, utility rates, manual meter entry, manual invoice calculation, tenant invoice view | First usable core system; first round of testing |
| Build 2 | 29/11 (end of Sprint 4) | Meter reading by photo (quality check, OCR, validation, manual fallback), automatic invoices, QR payment and payment status, reminders and notifications, anomaly alerts | Main AI features working; second round of testing |
| Build 3 | 13/12 (end of Sprint 5) | Issue reporting with AI triage, dashboard and reports, data export and deletion, bug fixes, optional extension features | Final product for demo and grading |

### Releases

### Project Schedule

The schedule is managed in Jira (one board, one epic per feature group, tasks assigned to members). The tables below are the initial plan; the Jira timeline screenshot is inserted here: [insert Jira roadmap screenshot]. Task owners use the role codes from section 3.2 and will be replaced by member names in Jira.

Sprint 1 (5/10 to 18/10): Inception, PA0 and PA1

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 1.1 | Form group and register | PM | 5/10 to 11/10 |
| 1.2 | Set up Jira, GitHub, Facebook group; create repository folders | PM, BE | 5/10 to 11/10 |
| 1.3 | Brainstorm and select project idea | All | 5/10 to 11/10 |
| 1.4 | Interview at least 5 users; keep notes and recordings | BA, All | 5/10 to 11/10 |
| 1.5 | Write project proposal | BA | 5/10 to 11/10 |
| 1.6 | Write project plan v1 | PM | 12/10 to 18/10 |
| 1.7 | Write vision document v1 | BA | 12/10 to 18/10 |
| 1.8 | Draw 3 to 6 UI sketches of the main screens | FE | 12/10 to 18/10 |
| 1.9 | Write two weekly reports (week 1 and week 2) | PM | 11/10 and 18/10 |
| 1.10 | Review documents and package PA1-Group[ID].zip | QA, PM | 17/10 to 18/10 |

Sprint 2 (19/10 to 1/11): Elaboration, PA2

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 2.1 | Update plan and vision using TA feedback | PM, BA | 19/10 to 22/10 |
| 2.2 | Write use case model and use case specifications for core features | BA | 19/10 to 29/10 |
| 2.3 | Write supplementary specification (non-functional requirements) | BA, QA | 22/10 to 29/10 |
| 2.4 | Decide architecture and tech stack; write initial architecture description | BE | 19/10 to 26/10 |
| 2.5 | Design initial database (ER diagram) | BE | 22/10 to 29/10 |
| 2.6 | Design wireframes for main screens and test them with 2 to 3 users | FE, BA | 22/10 to 30/10 |
| 2.7 | Prototype meter OCR with 10 sample photos (feasibility spike) | BE | 24/10 to 30/10 |
| 2.8 | Set up project skeleton, automatic build and staging deployment | BE, FE | 26/10 to 1/11 |
| 2.9 | Produce Build 0 and smoke test | All, QA | 30/10 to 1/11 |
| 2.10 | Weekly reports and PA2 package | PM | Weekly |

Sprint 3 (2/11 to 15/11): Elaboration, PA3

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 3.1 | Detailed design: class and sequence diagrams, API specification | BE, BA | 2/11 to 6/11 |
| 3.2 | Write test plan | QA | 2/11 to 8/11 |
| 3.3 | Implement accounts, roles and consent screen | BE, FE | 2/11 to 8/11 |
| 3.4 | Implement house, room and utility rate management | BE, FE | 4/11 to 10/11 |
| 3.5 | Implement tenant and contract management with encrypted ID number and masking | BE, FE | 6/11 to 12/11 |
| 3.6 | Implement manual meter entry and invoice calculation; tenant invoice view | BE, FE | 8/11 to 14/11 |
| 3.7 | Write test cases for implemented features | QA | 8/11 to 14/11 |
| 3.8 | Produce Build 1 and test it | All, QA | 14/11 to 15/11 |

Sprint 4 (16/11 to 29/11): Construction, PA4

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 4.1 | Fix bugs found in Build 1 | All | 16/11 to 19/11 |
| 4.2 | Meter photo flow: quality check on capture, OCR, validation against history, manual fallback | BE, FE | 16/11 to 25/11 |
| 4.3 | Collect at least 100 meter photos (good and bad conditions) and measure OCR accuracy | QA | 16/11 to 26/11 |
| 4.4 | Automatic invoice generation and delivery to tenants | BE, FE | 18/11 to 24/11 |
| 4.5 | VietQR payment display and payment status tracking | BE, FE | 22/11 to 27/11 |
| 4.6 | Reminders and notifications (overdue invoices, expiring contracts) | BE | 22/11 to 27/11 |
| 4.7 | Usage anomaly alerts | BE | 24/11 to 28/11 |
| 4.8 | Test Build 2 and write test report | QA, All | 27/11 to 29/11 |

Sprint 5 (30/11 to 13/12): Construction, PA5

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 5.1 | Issue reporting with photo and AI triage (category, urgency, safety tips) | BE, FE | 30/11 to 5/12 |
| 5.2 | Dashboard and reports with export | BE, FE | 30/11 to 6/12 |
| 5.3 | Data export and deletion on request; access log view | BE | 2/12 to 7/12 |
| 5.4 | Optional extension: monthly summary or message assistant (only if Build 2 is stable) | BE | 4/12 to 9/12 |
| 5.5 | Regression and system testing, final test report | QA, All | 7/12 to 12/12 |
| 5.6 | Write user guide and finalize all documents in /docs | QA, BA, PM | 5/12 to 12/12 |
| 5.7 | Produce Build 3, prepare and rehearse the demo | All | 11/12 to 13/12 |

### Project Resourcing

- People: five members, about 8 to 10 hours each per week, roughly 40 to 50 person-hours per week in total.

- Tools and services: free tiers of Jira, GitHub, cloud hosting and database.

- AI usage: third-party AI API with a daily request limit set by the team to avoid costs.

- Test resources: a set of at least 100 meter photos taken by the team, and phones with Android and iOS for testing.

## Project Monitoring and Control

- Sources: interviews with landlords and tenants, feedback from TAs, team analysis of existing apps.

- Documentation: high-level features (F01 to F16) are in the Vision document. Use cases and detailed requirements are stored in /docs/requirements from Sprint 2.

- Identification: each feature has an ID (F01...), each use case an ID (UC01...), and each requirement is a Jira issue.

- Prioritization: MoSCoW (Must, Should, Could). Must features are built first; AI extensions are Could.

- Traceability: Feature, use case, Jira task and test case are linked in a traceability table, updated at each sprint review.

- Baseline and change control: requirements are baselined on 1/11 (end of Sprint 2). After that, a change is raised as a Jira change request, the BA and PM assess its impact on schedule and scope, and it is approved at the next sprint planning. Urgent changes need agreement of the whole team.

- Status tracking: Jira statuses are To Do, In Progress, Done.

### Requirements Management

The requirements for this system are captured in the Vision document. Requested changes to requirements are captured in Change Requests, and are approved as part of the Configuration Management process.

### Reporting and Measurement

Updated cost and schedule estimates, and metrics summary reports, will be generated at the end of each iteration.

The Minimal Set of Metrics, as described in the RUP Guidelines: Metrics, will be gathered on a weekly basis.  These include:

Earned value for completed tasks. This is used to re-estimate the schedule and budget for the remainder of the project, and/or to identify need for scope changes.

Total defects open and closed – shown as a trend graph. This is used to help estimate the effort remaining to correct defects.

Acceptance test cases passing – shown as a trend graph. This is used to demonstrate progress to stakeholders.

In addition, overall costs will be monitored against the project budget.

### Risk Management

Risks will be identified in Inception Phase using the steps identified in the RUP for Small Projects activity “Identify and Assess Risks”. Project risk is evaluated at least once per iteration and documented in this table. The risks of the greatest magnitude are listed first in the table.

| Risk Ranking (High, Medium, Low) | Risk Description and Impact | Mitigation Strategy and/or Contingency Plan |
| --- | --- | --- |

| Risk Ranking (High, Medium, Low) | Risk Description and Impact | Mitigation Strategy and/or Contingency Plan |
| --- | --- | --- |
| R1 Probability: High Impact: High | Team lacks experience with the chosen technology, causing delays | Choose simple, well-documented technology; feasibility spike in Sprint 2; pair programming; weekly knowledge sharing. Contingency: cut scope to Must features Owner: PM |
| R2 Probability: Medium Impact: High | OCR is inaccurate on blurry, dark or reflective photos | Image-quality check at capture, validation against history, user confirmation, manual entry fallback; test with at least 100 photos Owner: BE |
| R3 Probability: Medium Impact: Medium | AI API cost, rate limits or outage | Use free tier, daily request cap, cache results, always keep manual fallback Owner: BE |
| R4 Probability: Medium Impact: High | Personal data or legal non-compliance | Collect minimum data, encrypt ID numbers, record consent, do not store ID card images, use synthetic data, check with instructor Owner: BA |
| R5 Probability: High Impact: Medium | Scope creep from extension ideas | MoSCoW priorities; extensions only after Build 2 is stable; change control process Owner: PM |
| R6 Probability: High Impact: Medium | Time conflicts with other courses and exams | Keep about 20% buffer per sprint; plan around exam weeks; tasks of at most 8 hours Owner: PM |
| R7 Probability: Medium Impact: High | A member is unavailable or contributes little | Visible workload in Jira; weekly check; reassign tasks; inform TAs early Owner: PM |
| R8 Probability: Medium Impact: Medium | Frontend and backend do not integrate smoothly | Agree on the API specification in Sprint 3; use mock API; integrate every week Owner: BE |
| R9 Probability: Medium Impact: Medium | Requirements are misunderstood because of few interviews | At least 5 interviews; test UI sketches and wireframes with users Owner: BA |
| R10 Probability: Low Impact: High | Lost code or merge conflicts | Pull request workflow; protected main branch; small commits Owner: BE |
| R11 Probability: Medium Impact: Medium | Free hosting limits or downtime during demo | Prepare a local demo environment and a recorded demo Owner: BE |

### Configuration Management

Appropriate tools will be selected which provide a database of Change Requests and a controlled versioned repository of project artifacts.

All source code, test scripts, and data files are included in baselines. Documentation related to the source code is also included in the baseline, such as design documentation. All customer deliverable artifacts are included in the final baseline of the iteration, including executables.