# Trozy — Smart Rental Management System

# Software Development Plan (Small Project)

# Version 2.0

# Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 18/10/2026 | 1.0 | Initial draft for the Inception phase (PA1). | Team 11 |
| 26/Oct/26 | 2.0 | Revised Section 3.2: Clarified team responsibilities, module ownership, and expected collaboration. | Trần Vinh Quang |
|  | 2.0 | Expanded the Project Manager's responsibilities to include direct development of advanced AI features B01–B05. | Trần Vinh Quang |
|  | 2.0 | Revised Section 4.1: Updated project effort estimates based on the existing five-sprint schedule, six-week implementation window, team capacity, and prioritized feature development. | Trần Vinh Quang |
|  | 2.0 | Revised Section 4.2.4: Clarified PA2 deliverables, updated AI feature development responsibilities, and added a B05 feasibility research task while preserving the original five-sprint schedule and major milestones. | Trần Vinh Quang |
|  | 2.0 | Updated Section 4.2.5: Clarified team resource allocation, AI development responsibilities, B05 long-term research scope, and resource monitoring while preserving the original five-sprint schedule. | Trần Vinh Quang |
|  | 2.0 | Revised Section 4.3: Updated feature identification and prioritization, clarified requirements change control, refined project monitoring metrics, adjusted AI-related risk responsibilities, and defined GitHub-based configuration management procedures. | Trần Vinh Quang |

# Table of Contents

1.	Introduction	4

1.1	Purpose	4

1.2	Scope	4

1.3	Overview	4

2.	Project Overview	5

2.1	Project Purpose, Scope, and Objectives	5

2.2	Assumptions and Constraints	6

2.3	Project Deliverables	6

3.	Project Organizations	6

3.1	Organizational Structure	6

3.2	Roles and Responsibilities	7

4.	Management Process	8

4.1	Project Estimates	8

4.2	Project Plan	10

4.2.1	Phase Plan	10

4.2.2	Iteration Objectives	11

4.2.3	Releases	12

4.2.4	Project Schedule	12

4.2.5	Project Resourcing	15

4.3	Project Monitoring and Control	15

4.3.1	Requirements Management	16

4.3.2	Reporting and Measurement	16

4.3.3	Risk Management	17

4.3.4	Configuration Management	18

# Software Development Plan (Small Project)

# Introduction

## Purpose

This document describes how our team plans, organizes and monitors the development of Trozy, a web application that helps boarding house landlords and tenants manage rooms, utility bills and maintenance requests with the help of AI.

This revised version (2.0) is prepared for Project Assignment 2 (PA2), building upon the initial Project Plan submitted during the Inception phase in PA1. It incorporates refinements to team responsibilities, project estimates, and iteration objectives while preserving the original five-sprint development schedule.

The purpose of the Software Development Plan is to gather all information necessary to control the project. It describes the approach to the development of the software and is the top-level plan generated and used by managers to direct the development effort.

The following people use the Software Development Plan:

- The project manager uses it to plan the project schedule and resource needs, and to track progress against the schedule.

- Project team members use it to understand what they need to do, when they need to do it, and what other activities they are dependent upon.

## Scope

The plan covers the whole project from 5/10/2026 to 13/12/2026, divided into five two-week sprints. It applies to all team members, and to all project documents and source code.

This Software Development Plan describes the overall plan to be used by the Trozy project, including deployment of the product. The details of the individual iterations will be described in the Iteration Plans.
The plans as outlined in this document are based upon the product requirements as defined in the Vision Document.

## Overview

Section 2 gives an overview of the project. Section 3 describes the team organization, roles and communication. Section 4 describes the phase plan, builds, schedule, requirements management and risk management.

This Software Development Plan contains the following information:

Project Overview — provides a description of the project's purpose, scope, and objectives.  It also defines the deliverables that the project is expected to deliver.

Project Organization — describes the organizational structure of the project team.

Definitions, Acronyms and Abbreviations

| Term | Meaning |
| --- | --- |
| AI | Artificial Intelligence |
| API | Application Programming Interface |
| Build | A tested version of the software deployed for testing |
| CCCD | Vietnamese citizen identity card number |
| MVP | Minimum Viable Product |
| OCR | Optical Character Recognition, reading text or digits from an image |
| PA | Project Assignment |
| PDPL | Vietnam Law on Personal Data Protection (2025) |
| PWA | Progressive Web App, a website that can be installed on a phone |
| RUP | Rational Unified Process (Inception, Elaboration, Construction phases) |
| Sprint | A two-week iteration in Scrum |
| TA | Teaching Assistant |
| VietQR | Standard QR code used for bank transfers in Vietnam |

References

- PA0: Group Registration and Tools Setup

- PA1: Project Assignment 1

- Project proposal and interview notes (PA0)

- Vision Document v1.0 (PA1)

- Law on Personal Data Protection 2025 (Law No. 91/2025/QH15) and Decree 356/2025/ND-CP

# Project Overview

## Project Purpose, Scope, and Objectives

Purpose. Many small landlords in Vietnam (roughly 5 to 30 rooms) still record electricity and water readings, calculate invoices and track payments with notebooks, Excel or Zalo messages. Doing this by hand each month is slow and error-prone, and mistakes lead to disputes with tenants. Existing apps cover most general management features, but not AI-assisted meter reading. Trozy fills this gap and adds further AI features that benefit both landlords and tenants.

Objectives.

| ID | Objective | Measure of success |
| --- | --- | --- |
| O1 | Deliver a working web app that covers the full monthly cycle: room, tenant, meter reading, invoice, payment | Full cycle demonstrated on test data at the end of Sprint 5 |
| O2 | Provide AI-assisted meter reading from photos | OCR with image-quality check, validation and manual fallback; target at least 90% correct reads on good-quality photos in our own test set of at least 100 photos |
| O3 | Provide AI differentiators: usage anomaly alerts and smart issue reporting | Both features demonstrated in the final build |
| O4 | Protect personal data by design | Minimum data collected; ID numbers encrypted; consent recorded; no ID card images stored |
| O5 | Practice professional teamwork | All tasks tracked in Jira, code merged through GitHub pull requests, weekly reports submitted on time |

In scope: account and role management; house, room, tenant and contract management; utility rate configuration; meter reading by photo; automatic invoices; QR payment tracking; reminders and notifications; anomaly alerts; issue reporting with AI triage; dashboard and reports; privacy functions.

Out of scope: real payment gateway integration, electronic contracts with digital signatures, in-app chat, storing images of ID cards, native mobile apps (stretch goal only).

## Assumptions and Constraints

Assumptions

- Team members are beginners in software development and will learn the technology during the project.

- Each member can spend about 8 to 10 hours per week on the project.

- Free tiers of cloud hosting and AI APIs are enough for development and demo.

- Only synthetic (fake) data is used for testing and demo.

Constraints

- Fixed deadlines: PA1 on 18/10, final build on 13/12/2026.

- Team of 3 to 5 students and zero budget.

- Mandatory tools: Moodle, Facebook group, Jira, GitHub with the required folder structure.

- Compliance with Vietnamese personal data protection law.

## Project Deliverables

| Assignment | End of | Main deliverables |
| --- | --- | --- |
| PA1 | Sprint 1 (18/10) | Project plan v1, Vision document v1, 3 to 6 UI sketches, 2 weekly reports |
| PA2 | Sprint 2 (1/11) | Updated plan and vision, requirements (use cases), initial architecture and design, Build 0 |
| PA3 | Sprint 3 (15/11) | Detailed design, test plan, Build 1 |
| PA4 | Sprint 4 (29/11) | Build 2, test cases and test report |
| PA5 | Sprint 5 (13/12) | Final build, final documents, user guide, demo |

Evolution of the Project Plan

The plan is reviewed at every sprint planning meeting and updated when scope, schedule or team changes. The version after TA feedback will be submitted in PA2. Every change is recorded in the revision history and the old version stays in GitHub (/docs/management).

# Project Organization

## Organizational Structure

The team is flat and self-organized, following Scrum. The group leader acts as Project Manager and Scrum Master. One member acts as Product Owner for requirements and priorities. All members take part in development and testing. The instructor and TAs act as reviewers and approve the project direction.

External Interfaces and Communication

| Party | Interaction | Channel | Frequency |
| --- | --- | --- | --- |
| Instructor and TAs | Review proposal and deliverables, give feedback | Moodle, lab sessions | Every sprint |
| Potential users (landlords, tenants) | Interviews, feedback on UI sketches and builds | Meetings, calls, forms | At least 5 interviews in Sprint 1, feedback each sprint |
| AI service provider | Vision and language API used for meter reading and issue triage | HTTPS API | Runtime |

Tools

| Tool | Purpose |
| --- | --- |
| Moodle | Submit assignments |
| Facebook group | Class announcements and Q&A |
| Jira | One board for the group, tasks organized in sprints |
| GitHub | Source control with folders /src, /docs (management, requirements, analysis and design, test) and /pa |

Team meetings and tracking. Sprint planning on the first day of each sprint (1 hour). Two short team meetings per week (30 minutes) to review the board and risks. Daily progress notes in the Zalo channel. Sprint review and retrospective on the last day. One weekly report per week, stored in /docs/management. Progress is read from the Jira board.

## Roles and Responsibilities

The project team consists of five members, each assigned a primary role with clearly defined responsibilities. Members collaborate across requirements analysis, design, implementation, testing, and project management. Each member is accountable for their assigned deliverables and may contribute to other activities when necessary.

| Person | Role |
| --- | --- |
| Trần Vinh Quang, Group Leader | Project Manager, Scrum Master & AI Features Development Lead (PM). Responsible for project planning, task assignment, milestone scheduling, progress monitoring, risk management, team coordination, and communication with TAs. Maintains the Jira board, consolidates weekly reports, and reviews assignment deliverables. Additionally, directly leads the research, design, and implementation of four advanced features: B01 – AI Operations Copilot; B02 – Utility Anomaly Detection; B03 – Smart OCR for Meters and Documents; and B04 – AI-Based Maintenance Issue Classification. Also responsible for the feasibility research and experimental investigation of B05 – Debt, Revenue, and Vacancy Forecasting, as a long-term development feature. Coordinates with Backend and Frontend developers for feature integration and collaborates with QA to verify functionality and reliability. |
| Phạm Đặng Thiên Quốc | Product Owner & Business Analyst (BA). Responsible for gathering, analyzing, and prioritizing functional and non-functional requirements across all system modules (M01–M23). Maintains the Vision Document, defines business rules, develops use-case diagrams and specifications, and validates system workflows. Works with the PM to define feature priorities, clarify requirements for advanced AI features, and ensure consistency between requirements, UI designs, and implementation. |
| Phạm Nguyễn Trường Huy | Software Architect & Backend Developer (BE). Responsible for system architecture, database design, API development, authentication, authorization, and backend implementation. Primarily develops business logic and services for property and tenant management (M01–M05), billing and financial operations (M06–M11), tenant services and operations (M12–M19), and reporting and configuration (M20–M21). Supports the PM in integrating AI features with backend APIs, databases, and existing business workflows. |
| Nguyễn Đức Dũng | Frontend & UI/UX Developer (FE). Responsible for UI/UX design, wireframes, interactive prototypes, responsive web interfaces, and frontend implementation. Develops the Landlord Dashboard and Tenant Portal, including interfaces for property management, contracts, utilities, invoices, payments, maintenance requests, and reporting (M01–M21). Integrates backend APIs and collaborates with the PM to develop interfaces for AI-assisted features (B01–B04). Ensures usability, consistency, and appropriate error handling. |
| Đặng Biên Phúc Lâm | Tester & Documentation Engineer (QA). Responsible for preparing test plans, test cases, test data, and test execution reports. Performs functional, integration, regression, and business-rule testing across all implemented modules. Verifies role-based access control, financial calculations, invoice processing, and operational workflows. Collaborates with the PM to evaluate AI/OCR outputs and any optional B05 experimental results, where applicable, reports defects through Jira, and reviews project documents for completeness and consistency. |

Shared Responsibilities

All members participate in team meetings, requirements reviews, peer reviews, and defect resolution. The PM coordinates overall project delivery and leads the development of B01–B04 and the feasibility research of B05, while the BA, Backend, Frontend, and QA members provide domain-specific support for integration and validation. Each task is tracked in Jira with an assigned owner, deadline, and progress status.

# Management Process

## Project Estimates

The Trozy – Smart Rental Management System is developed by Team 11, consisting of five members. The project follows the five-sprint development schedule established in PA1, covering ten weeks from October 5 to December 13, 2026.

Sprint 1 focuses on project initiation and initial planning. Sprint 2 focuses on requirements refinement, use-case modeling, and UI prototyping. The remaining three sprints (Sprints 3–5), covering six weeks, are allocated primarily to software implementation, integration, testing, and final delivery.

Effort Estimation

The team adopts a capacity-based estimation approach. Assuming an average availability of approximately 8–10 hours per member per week, the estimated nominal development capacity for the final six weeks is 240–300 person-hours.

The following table presents the preliminary upper-bound effort allocation under the full-capacity scenario of 300 person-hours. These allocations represent planning limits rather than guaranteed workload commitments.

| Work Package | Upper-bound Effort Allocation (Person-hours) | Primary Roles |
| --- | --- | --- |
| System Architecture, Database, and Security Foundation | 45 | BE |
| Core Rental Management (M01–M05) | 40 | BE, FE |
| Billing and Financial Management (M06–M11) | 55 | BE, FE |
| Tenant Services and Operations (M12–M19) | 30 | BE, FE |
| Reporting and Configuration (M20–M21) | 15 | BE, FE |
| Intelligent Features (M22–M23, B01–B05) | 50 | PM, BE, FE |
| Integration, Testing, and Defect Resolution | 45 | QA, Team |
| Release Preparation and Project Coordination | 20 | PM, Team |
| Total Upper-bound Capacity | 300 | All Members |

The effort figures presented above represent preliminary upper-bound allocations for individual work packages rather than guaranteed task-level commitments. Actual sprint workloads will be planned according to team availability, technical dependencies, and feature priorities, with approximately 20% of available capacity reserved for unexpected issues and schedule risks. This contingency is included within the total available capacity and is not added on top of the 300-person-hour upper bound.

Core rental management workflows and release-critical testing will receive priority. B02–B04 will be developed according to the planned release objectives, while B01 is a limited, capacity-dependent enhancement. B05 is restricted to feasibility research and optional experimentation, with full implementation reserved for future development.

Schedule Estimation

The project schedule remains consistent with the five sprints defined in PA1:

- Sprint 1 (October 5–18): Project initiation, scope definition, initial planning, and PA1 deliverables.

- Sprint 2 (October 19–November 1): Requirements refinement, use-case specifications, UI prototypes, and PA2 deliverables.

- Sprint 3 (November 2–15): System architecture, database design, and initial functional implementation.

- Sprint 4 (November 16–29): Extended business functionality, system integration, and development of prioritized intelligent features.

- Sprint 5 (November 30–December 13): Final feature integration, testing, defect resolution, stabilization, and project demonstration.

The detailed sprint tasks, deliverables, and milestones are maintained in Section 4.2 and the Jira project schedule.

Cost Estimation

The project primarily uses free or educational development tools to minimize direct monetary costs. Potential expenses include hosting, databases, and external AI/OCR services if free-tier limitations are exceeded.

No direct salary expenses are planned. Team effort is estimated in person-hours for workload planning and project monitoring.

Estimation Assumptions

- The team consists of five members with responsibilities defined in Section 3.2.

- The six-week implementation capacity is provisionally estimated using 8–10 working hours per member per week.

- Requirements analysis and initial UI prototyping are primarily conducted during Sprint 2.

- Core rental management workflows take priority over nonessential enhancements.

- Development tasks may be performed in parallel when technical dependencies allow.

- The development of B01–B04 is led by the PM with support from relevant technical members. B05 is limited to feasibility research and optional experimentation, while its full implementation is reserved for future development.

- The planned implementation depth must remain consistent with the priorities and scope defined in the Vision Document.

Re-estimation and Control

Project estimates will be reviewed at the end of each sprint based on actual task completion, remaining effort, and available resources.

Re-estimation will also occur when significant requirement changes, technical risks, data limitations, or integration difficulties affect the original plan.

If the remaining effort exceeds the team's available capacity, the Project Manager will coordinate task redistribution or propose scope and priority adjustments. Any approved scope changes will be reflected consistently in the Project Plan and Vision Document.

## Project Plan

The project follows the five two-week sprints established in the initial Project Plan (PA1). The revised plan retains the original sprint boundaries and software build milestones while refining phase objectives, release criteria, resource allocation, and advanced feature development responsibilities.

The detailed functional scope is defined in the Trozy Vision Document. Task execution and progress are tracked through Jira.

### Phase Plan

The project has three phases and five sprints, consistent with the course schedule.

| Phase | Sprints | Dates | Objectives | Milestone |
| --- | --- | --- | --- | --- |
| Inception | Sprint 1 | 5/10 to 18/10 | Form the team, set up tools, choose the project, interview users, write initial plan, vision and UI sketches | Agreed vision, scope and plan (PA1) |
| Elaboration | Sprint 2, Sprint 3 | 19/10 to 15/11 | Define requirements, design architecture and database, write test plan, build the core of the system | Requirements baselined, architecture proven by a working build (PA2, PA3) |
| Construction | Sprint 4, Sprint 5 | 16/11 to 13/12 | Implement AI features and the remaining functions, test, fix bugs, finish documents | Final tested product and demo (PA4, PA5) |

### Iteration Objectives

Each sprint has specific objectives and expected outcomes to support incremental development. The following table summarizes the objectives of the five sprints established in the initial Project Plan.

| Sprint | Main Objectives | Expected Outcomes |
| --- | --- | --- |
| Sprint 1 | Define project scope, organize the team, establish development tools, and prepare initial documentation. | PA0, PA1, initial Vision and Project Plan. |
| Sprint 2 | Refine requirements, develop use-case specifications and UI prototypes, and establish the technical foundation. | PA2 deliverables and Build 0. |
| Sprint 3 | Finalize system architecture and implement core rental management functionality. | Architecture design, database design, and Build 1. |
| Sprint 4 | Extend financial workflows and integrate OCR-assisted meter reading and anomaly detection. | Build 2 and initial AI integration. |
| Sprint 5 | Complete maintenance workflows, reporting, prioritized advanced AI features, testing, and final delivery. | Build 3, final test report, documentation, and demonstration. |

We will produce four builds. Each build is created from the main branch, tagged in GitHub, deployed to a staging environment and checked with a smoke test before the team tests it.

| Build | Date | Content | Purpose |
| --- | --- | --- | --- |
| Build 0 | 1/11 (end of Sprint 2) | Technical skeleton: sign up, login, role-based home page, one working CRUD (rooms), database, automatic build | Prove that the chosen technology works end to end |
| Build 1 | 15/11 (end of Sprint 3) | Accounts and roles with consent, house and room management, tenant and contract management, utility rates, manual meter entry, manual invoice calculation, tenant invoice view | First usable core system; first round of testing |
| Build 2 | 29/11 (end of Sprint 4) | Meter reading by photo (quality check, OCR, validation, manual fallback), automatic invoices, QR payment and payment status, reminders and notifications, anomaly alerts | Main AI features working; second round of testing |
| Build 3 | 13/12 (end of Sprint 5) | Issue reporting with AI triage, dashboard and reports, data export and deletion, bug fixes, optional extension features | Final product for demo and grading |

Advanced Feature Development

The PM/AI Features Development Lead is responsible for the development of B01–B04 and the feasibility research of B05. B02 (Utility Anomaly Detection) and B03 (Smart OCR) are planned for Build 2, B02 (Utility Anomaly Detection) and B03 (Smart OCR) are planned for Build 2. B04 (AI-Based Maintenance Issue Classification) is planned for Build 3, whereas a limited MVP of B01 (AI Operations Copilot) is considered an optional extension, subject to Build 2 stability and available resources. B05 (Debt, Revenue, and Vacancy Forecasting) is classified as an experimental and long-term development feature. During the current project, the team may investigate forecasting methods, evaluate historical data requirements, and optionally develop a proof of concept. Full implementation and integration of B05 are reserved for future development and are not mandatory deliverables of Build 3.

The advanced features will extend existing system modules rather than duplicate their functionality.

### Releases

The project follows an incremental release strategy aligned with the original five-sprint schedule. Four software builds (Build 0–Build 3) are planned to demonstrate technical feasibility, validate core functionality, integrate advanced features, and prepare the final system for evaluation.

Each build will be maintained in GitHub and verified through appropriate testing before demonstration.

| Release | Target Date | Release Type | Purpose and Acceptance Criteria |
| --- | --- | --- | --- |
| Build 0 | 01/11/2026 | Technical Prototype | Validate the technology stack, database connectivity, authentication, and basic room management operations. The technical foundation must be demonstrable. |
| Build 1 | 15/11/2026 | Initial Functional Release | Deliver the essential rental management workflows, including accounts, properties, rooms, tenants, contracts, manual meter readings, and invoice calculations. Core workflows must pass initial functional tests. |
| Build 2 | 29/11/2026 | Integrated Feature Release | Extend the system with automatic invoicing, VietQR payment instructions, payment status tracking, OCR-assisted meter readings (B03), and utility anomaly detection (B02). Integrated workflows must be tested, and OCR results must support user verification and manual correction. |
| Build 3 | 13/12/2026 | Final Demonstration Release | Deliver the integrated system with maintenance management, AI-assisted issue classification (B04), dashboards, reporting, final defect fixes, and a limited AI Operations Copilot (B01) if feasible. Critical planned workflows must pass final verification before demonstration. |

Advanced Feature Release Scope

B01–B04 are developed incrementally according to the planned sprint priorities and available resources.

B05 (Debt, Revenue, and Vacancy Forecasting) is classified as an experimental and long-term development feature. Feasibility research and optional proof-of-concept activities may be conducted during the project, but full implementation and integration of B05 are not required for Build 3.

Release Verification

Each release will undergo relevant functional, integration, and smoke testing. Identified defects will be tracked in Jira. The Project Manager will coordinate release reviews and confirm readiness based on the agreed scope and testing results.

### Project Schedule

The project schedule is managed through Jira, with tasks organized by sprint and feature group. The revised schedule retains the original five-sprint timeline established in PA1 while clarifying PA2 deliverables, updating technical responsibilities, and incorporating advanced AI feature development activities.

Task owners are identified using the role codes defined in Section 3.2. The Jira board provides detailed task assignments, dependencies, progress status, and updates throughout project execution.

Sprint 1 (5/10 to 18/10): Inception, PA0 and PA1

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 1.1 | Form group and register | PM | 5/10 to 11/10 |
| 1.2 | Set up Jira, GitHub, Facebook group; create repository folders | PM, BE | 5/10 to 11/10 |
| 1.3 | Brainstorm and select project idea | All | 5/10 to 11/10 |
| 1.4 | Interview at least 5 users; keep notes and recordings | BA, All | 5/10 to 11/10 |
| 1.5 | Write project proposal | BA | 5/10 to 11/10 |
| 1.6 | Write project plan v1 | PM | 12/10 to 18/10 |
| 1.7 | Write vision document v1 | BA | 12/10 to 18/10 |
| 1.8 | Draw 3 to 6 UI sketches of the main screens | FE | 12/10 to 18/10 |
| 1.9 | Write two weekly reports (week 1 and week 2) | PM | 11/10 and 18/10 |
| 1.10 | Review documents and package PA1-Group[ID].zip | QA, PM | 17/10 to 18/10 |

Sprint 2 (19/10 to 1/11): Elaboration, PA2

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 2.1 | Update plan and vision using TA feedback | PM, BA | 19/10 to 22/10 |
| 2.2 | Complete use-case diagrams and specifications for every use case included in the use-case model, ensuring consistency with the revised Vision Document. | BA, QA (review) | 19/10 to 29/10 |
| 2.3 | Write supplementary specification (non-functional requirements) | BA, QA | 22/10 to 29/10 |
| 2.4 | Decide architecture and tech stack; write initial architecture description | BE | 19/10 to 26/10 |
| 2.5 | Design initial database (ER diagram) | BE | 22/10 to 29/10 |
| 2.6 | Design UI prototypes covering at least three key use cases and review them with 2–3 users where feasible. | FE, BA | 22/10 to 30/10 |
| 2.7 | Prototype OCR-assisted meter reading using 10 sample photos (B03 feasibility spike). | PM, BE | 24/10 to 30/10 |
| 2.8 | Set up project skeleton, automatic build and staging deployment | BE, FE | 26/10 to 1/11 |
| 2.9 | Produce Build 0 and smoke test | All, QA | 30/10 to 1/11 |
| 2.10 | Prepare weekly reports, review PA2 deliverables for consistency, and package the PA2 submission. | PM, QA | Weekly |

Sprint 3 (2/11 to 15/11): Elaboration, PA3

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 3.1 | Detailed design: class and sequence diagrams, API specification | BE, BA | 2/11 to 6/11 |
| 3.2 | Write test plan | QA | 2/11 to 8/11 |
| 3.3 | Implement accounts, roles and consent screen | BE, FE | 2/11 to 8/11 |
| 3.4 | Implement house, room and utility rate management | BE, FE | 4/11 to 10/11 |
| 3.5 | Implement tenant and contract management with encrypted ID number and masking | BE, FE | 6/11 to 12/11 |
| 3.6 | Implement manual meter entry and invoice calculation; tenant invoice view | BE, FE | 8/11 to 14/11 |
| 3.7 | Write test cases for implemented features | QA | 8/11 to 14/11 |
| 3.8 | Produce Build 1 and test it | All, QA | 14/11 to 15/11 |

Sprint 4 (16/11 to 29/11): Construction, PA4

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 4.1 | Fix bugs found in Build 1 | All | 16/11 to 19/11 |
| 4.2 | Implement OCR-assisted meter reading (B03), including image-quality checks, validation, user confirmation, and manual fallback. | PM, BE, FE | 16/11 to 25/11 |
| 4.3 | Collect at least 100 meter photos (good and bad conditions) and measure OCR accuracy | QA | 16/11 to 26/11 |
| 4.4 | Automatic invoice generation and delivery to tenants | BE, FE | 18/11 to 24/11 |
| 4.5 | VietQR payment display and payment status tracking | BE, FE | 22/11 to 27/11 |
| 4.6 | Reminders and notifications (overdue invoices, expiring contracts) | BE | 22/11 to 27/11 |
| 4.7 | Implement utility consumption anomaly detection and alerts (B02). | PM, BE | 24/11 to 28/11 |
| 4.8 | Test Build 2 and write test report | QA, All | 27/11 to 29/11 |

Sprint 5 (30/11 to 13/12): Construction, PA5

| ID | Task | Owner | Dates |
| --- | --- | --- | --- |
| 5.1 | Implement maintenance issue reporting with AI-assisted classification and prioritization (B04), including category, urgency, and suggested actions. | PM, BE, FE | 30/11 to 5/12 |
| 5.2 | Dashboard and reports with export | BE, FE | 30/11 to 6/12 |
| 5.3 | Data export and deletion on request; access log view | BE | 2/12 to 7/12 |
| 5.4 | Optional extension: develop a limited AI Operations Copilot (B01) for authorized operational queries or monthly summaries, only if Build 2 is stable. | PM, BE, FE | 4/12 to 9/12 |
| 5.5 | Regression and system testing, final test report | QA, All | 7/12 to 12/12 |
| 5.6 | Write user guide and finalize all documents in /docs | QA, BA, PM | 5/12 to 12/12 |
| 5.7 | Produce Build 3, prepare and rehearse the demo | All | 11/12 to 13/12 |
| 5.8 | Investigate forecasting methods and historical data requirements for B05; document feasibility findings and optionally develop an experimental proof of concept. | PM | 04/12–09/12 |

### Project Resourcing

- People: The project team consists of five members, each contributing approximately 8–10 hours per week, resulting in an estimated team capacity of 40–50 person-hours per week. During the six-week primary implementation period (Sprints 3–5), the nominal capacity is approximately 240–300 person-hours. Actual workload allocation will consider member availability, task dependencies, and contingency time.

- Team Responsibilities: Resources are allocated according to the roles defined in Section 3.2. The PM manages project planning, coordination, and progress monitoring while directly leading B01–B04 development. The BA handles requirements and business rule validation; the BE develops backend services, APIs, and databases; the FE implements user interfaces and system integration; and QA handles testing and quality verification. Members collaborate on shared tasks when necessary.

- Advanced AI Features: B01–B04 are developed incrementally under the leadership of the PM, with technical support from Backend, Frontend, and QA members. B05 is limited to feasibility research and optional experimentation. Its complete implementation and integration are reserved for future development.

- Tools and Services: The team uses free or educational versions of Jira, GitHub, cloud hosting, database services, and development tools whenever feasible.

- AI Usage: Third-party AI APIs may be used for OCR, anomaly analysis, operational assistance, and maintenance classification. Usage limits will be configured to minimize costs, and manual alternatives will be maintained for relevant workflows when AI services are unavailable.

- Test Resources: The team will prepare meter photographs under different image-quality conditions, including a suitable test set for evaluating OCR accuracy against NFR-05 in the Vision Document. Android and iOS devices will be used to evaluate mobile browser compatibility and responsive interfaces.

- Resource Monitoring: The PM reviews team availability and workload at sprint planning and review meetings. Task assignments may be adjusted when workload imbalances, technical difficulties, or schedule risks are identified. Essential rental management functions and release-critical testing receive priority over optional enhancements.

## Project Monitoring and Control

- Sources: Interviews with landlords and tenants, feedback from TAs, team analysis of existing apps.

- Documentation: High-level system modules (M01–M23) and advanced features (B01–B05) are documented in the Vision Document. Use-case models, specifications, and detailed requirements are maintained in /docs/requirements. The implementation scope and priorities are defined consistently with the Project Plan.

- Identification: System modules use identifiers M01–M23, advanced features use B01–B05, and use cases use unique identifiers such as UC01, UC02, etc. Implementation tasks and change requests are tracked through Jira issues.

- Prioritization: The project applies MoSCoW prioritization. Core rental management workflows and the planned AI features B02–B04 are prioritized according to their dependencies and release objectives. B01 is planned as a limited, capacity-dependent enhancement. B05 is classified as a future development feature, with only feasibility research and optional experimentation included in the current project. Scope changes are reviewed by the PM and BA.

- Traceability: Feature, use case, Jira task and test case are linked in a traceability table, updated at each sprint review.

- Baseline and change control: Requirements are baselined on 1/11 (end of Sprint 2). After that, a change is raised as a Jira change request, the BA and PM assess its impact on schedule and scope, and it is approved at the next sprint planning. Urgent changes need agreement of the whole team.

- Status tracking: Jira statuses are To Do, In Progress, Done.

### Requirements Management

The project requirements are defined in the Vision Document and detailed through use-case specifications and supplementary requirements. The Business Analyst (BA) is responsible for maintaining requirement consistency, while the Project Manager (PM) coordinates requirement prioritization and change control.

Requirements are reviewed and baselined at the end of Sprint 2. Any proposed change after the baseline is recorded as a Jira change request, including its description, rationale, priority, and expected impact.

The BA and PM evaluate the change in terms of scope, development effort, schedule, dependencies, and project risks. Changes are approved through team agreement before being incorporated into the relevant sprint plan.

Approved changes are reflected in the Vision Document, use-case specifications, Jira tasks, and test cases when applicable. Requirement traceability is maintained to ensure that implemented features remain consistent with the agreed project scope.

B05 remains a future development feature. Requests for its full implementation will be evaluated separately and are not included in the committed Build 3 scope.

### Reporting and Measurement

Project progress is monitored through Jira, GitHub, weekly reports, and testing records. The PM reviews project status during team meetings and at the end of each sprint.

The following metrics are used to evaluate project progress and quality:

- Sprint Task Completion: The number and percentage of planned sprint tasks completed, based on Jira task status.

- Defect Tracking: The number of open, resolved, and critical defects identified during testing.

- Test Execution Results: The number of passed, failed, and blocked test cases for implemented functionality.

- Effort Tracking: Planned and actual person-hours are compared when reliable effort data is available.

- Release Readiness: Each build is reviewed against its planned functional scope and testing requirements before demonstration or delivery.

Weekly reports summarize completed work, ongoing tasks, encountered difficulties, and planned activities for the following week.

At each sprint review, the PM and team evaluate schedule deviations, unresolved defects, technical risks, and remaining capacity. Corrective actions may include task reassignment, defect prioritization, or approved scope adjustments.

External service expenses are monitored where applicable, while team effort is tracked in person-hours rather than salary costs.

### Risk Management

Risks will be identified in Inception Phase using the steps identified in the RUP for Small Projects activity “Identify and Assess Risks”. Project risk is evaluated at least once per iteration and documented in this table. The risks of the greatest magnitude are listed first in the table.

| Risk ID / Probability / Impact | Risk Description and Impact | Mitigation Strategy and/or Contingency Plan |
| --- | --- | --- |
| R1 Probability: High Impact: High | Team lacks experience with the chosen technology, causing delays | Choose simple, well-documented technology; feasibility spike in Sprint 2; pair programming; weekly knowledge sharing. Contingency: cut scope to Must features Owner: PM |
| R2 Probability: Medium Impact: High | OCR is inaccurate on blurry, dark or reflective photos | Image-quality check at capture, validation against history, user confirmation, manual entry fallback; test with at least 100 photos Owner: PM, BE, QA |
| R3 Probability: Medium Impact: Medium | AI API cost, rate limits or outage | Use free tier, daily request cap, cache results, always keep manual fallback Owner: PM, BE |
| R4 Probability: Medium Impact: High | Personal data or legal non-compliance | Collect minimum data, encrypt ID numbers, record consent, do not store ID card images, use synthetic data, check with instructor Owner: BA |
| R5 Probability: High Impact: Medium | Scope creep from extension ideas | Apply MoSCoW prioritization and formal change control. Prioritize committed rental management workflows and planned B02–B04 development. Keep B01 within a limited scope and B05 as feasibility research and optional experimentation. Defer nonessential enhancements when release-critical work is at risk. Contingency: Reassess and reduce optional scope before changing committed build objectives. Owner: PM |
| R6 Probability: High Impact: Medium | Time conflicts with other courses and exams | Keep about 20% buffer per sprint; plan around exam weeks; tasks of at most 8 hours Owner: PM |
| R7 Probability: Medium Impact: High | A member is unavailable or contributes little | Visible workload in Jira; weekly check; reassign tasks; inform TAs early Owner: PM |
| R8 Probability: Medium Impact: Medium | Frontend and backend do not integrate smoothly | Agree on the API specification in Sprint 3; use mock API; integrate every week Owner: BE |
| R9 Probability: Medium Impact: Medium | Requirements are misunderstood because of few interviews | At least 5 interviews; test UI sketches and wireframes with users Owner: BA |
| R10 Probability: Low Impact: High | Lost code or merge conflicts | Pull request workflow; protected main branch; small commits Owner: BE |
| R11 Probability: Medium Impact: Medium | Free hosting limits or downtime during demo | Prepare a local demo environment and a recorded demo Owner: BE |

### Configuration Management

GitHub is used as the central version-control repository for the Trozy project. It stores source code, project documentation, requirements, design artifacts, testing materials, and official project assignment deliverables.

Project artifacts are organized using the repository structure defined in Section 3.1, including /src for source code, /docs for project documents, and /pa for assignment submissions.

Code changes are submitted through GitHub branches and pull requests for review before being merged into the main branch. Each planned software build (Build 0–Build 3) is associated with an identifiable GitHub version or release tag.

Project documents are maintained with version numbers and revision histories. Updated versions of the Project Plan, Vision Document, use-case specifications, and testing artifacts are committed to GitHub to preserve change history.

Jira is used to manage tasks, defects, and change requests. Approved requirement or scope changes are reflected in the relevant project documents, implementation tasks, and testing materials.

Official assignment submissions are preserved separately from working documents. Configuration baselines are reviewed at appropriate sprint milestones to ensure consistency between source code, documentation, and released builds.

Sensitive credentials, private personal information, and production secrets must not be committed to the repository.